## Sheet2
COP 23-Y2 Quarterly Activity Spend Plan for MoHSS COAG Activities
Program Cluster :
Program:
Period: June 2025 to September 2025
Acivity | Budget Line | Budget Amount | Implementation Date | Number of Participants | Town, Region | Activity Request Memo Status | Recommendation
A 3-day workshop for 30 participants to validate the Data Access and Use Guideline and Data Archiving SOP. | [6 empty] | Drop
System Process Alignment & Reengineering: Review and align systems (EDT, EPMS, e-Notification) | [6 empty] | Drop
Integrated Health Statistical Report Compilation. | Q3HISEP&RS07, Q4HISEP&RS04 | 5936 | August | 30 | WINDHOEK | Not started | Prioritize
Data Quality Assessment: Systematic evaluation of data quality issues across tools to identify gaps. |  | Not costed | August | - | WINDHOEK |  | Prioritize
Development of a SharePoint/common platform to streamline data sharing. |  | Not costed | September | - | WINDHOEK |  | Prioritize
National Technical Support Visits: Regional visits shared among three programs | Q1HISEP&RS01, Q4HISEP&RS01 | 3008 | July | 4 per regions | 12 regions | Drafted | Prioritized
National Data Warehouse Hackathon | Q2HISEP&RS13 | 4932.79 | August | 10 | Windhoek | Not started | Prioritised
DHIS2 server side administrator training | New Activity |  | September | 10 | Windhoek | Not started | Prioritize
DHIS2 training, interface has changed there is a need for training on the extraction of data from DHIS too Data extraction, data quality checks, and basic pivot data analysis. On Programs Subnational participants such as PMTCT, Subnational participants regional HIS officers, family health | New activity |  | August | Cluster 1 7 regions 30 Cluster 2 7 Regions 30 total: 60 | Erongo, Otjiwarongo | Not started | Prioritize
Ptracker refresher training | New activity |  | September | Cluster 1 7 regions 30 Cluster 2 7 Regions 30 total: 60 | Windhoek, Oshana | Not started | Prioritize